## Slide 1
EasyCLA → LFX Self Serve Integration
Migration program — architecture review & scope approval
Spec: specs/001-easycla-ss-integration-fable · branch 001-easycla-ss-integration · July 2026

## Slide 2
GOAL
What we want to do, and why
• Consolidate EasyCLA's three user-facing UIs into LFX Self Serve (LFX One)
  – Contributor Console → Me lens (view + sign ICLAs/ECLAs)
  – Corporate CLA Console → Organization lens (CCLA management)
  – PCC EasyCLA module → Project lens (CLA groups, repos, templates)
• Feature parity is the contract — inventory-driven checklists per milestone
• Separately gated decision: re-platform the EasyCLA API as a V2 Kubernetes service, optionally DynamoDB → Postgres
• Every milestone independently shippable and reversible (config-flip cutovers)

## Slide 3
WHERE WE ARE
Current state (verified in code)
• Two Go backends, both AWS Lambdas: /v3 + /v4 (cla-backend-go) and legacy /v1 + /v2 (cla-backend-legacy — Python is fully removed)
• Already routed through lfx-gateway (/cla-service/*) — gateway onboarding is done
• ~19 DynamoDB tables (us-east-1); signed PDFs in S3 with 15-min presigned URLs
• DocuSign lives entirely in the backend (v2/sign): consoles only redirect to a sign_url
• PR check remediation link is an SSM parameter → console cutover/rollback is a config flip
• LF SSO login is already mandatory in both consoles (incl. ICLA) — no anonymous flow remains
• Roles (cla-manager / cla-signatory / designee) hardcoded in ACS (Salesforce-backed); no CLA types in OpenFGA yet

## Slide 4
WHERE WE ARE GOING
Target platform: Self Serve + LFX V2
• Self Serve: Angular 20 + Express SSR; lens-scoped modules (Me / Organization / Project / Foundation)
• Integration pattern already proven: crowdfunding = external backend behind SS server routes with own token audience
• M1–M5: SS becomes a client of the existing EasyCLA v3/v4 APIs — no business-logic rewrite, enforcement stays in EasyCLA
• “V2 service” = Helm/ArgoCD, Heimdall authN, OpenFGA authZ, NATS, OTel — ~15 services follow this shape today
• Roles: bridge to EasyCLA/ACS until M6; model CLA in OpenFGA only when enforcement itself moves
• No DocuSign integration in SS, ever — request sign_url, redirect, done (no bridge service needed)

## Slide 5
ROADMAP
Six milestones
# | Milestone | Retires | Effort
M1 | Read-only “My CLAs” in Me lens | — | S
M2 | Sign ICLA in SS (M2a GitHub / M2b GitLab / M2c Gerrit) | — | M
M3 | Corporate flow + ECLA in SS (M3a–c) | Contributor Console | L
M4 | CCLA management in Organization lens | Corporate Console + its GraphQL BFF | XL
M5 | EasyCLA admin in Project lens | PCC EasyCLA module | L
M6 | API → Kubernetes V2 service (± Postgres) | Lambda stacks (decision milestone) | XL / XXL
M1–M3 build the contributor path in increasing complexity; M4/M5 parallelize after M3; M6 gated on separate go/no-go.

## Slide 6
MILESTONE 1
M1 — Read-only “My CLAs” (Me lens) · Effort: S
• First self-service view of a contributor's CLA history anywhere (ICLAs + valid ECLAs, ICLA PDF download)
• Builds the plumbing every later milestone reuses: SS server 'cla' module + identity mapping
• Identity = union of three keys: LF username + verified emails + linked GitHub accounts (numeric ID)
  – “Don't see your CLAs? Link your GitHub account” CTA into SS's existing identity-linking flow
  – One small EasyCLA read endpoint expected (GET /v4/users/by-identity) — existing search API is a table scan
• Read-only, feature-flagged, zero writes — trivially reversible
• Exit: 100% parity vs backend data on sample; PDF success ≥ 99%; unmatched-identity telemetry live

## Slide 7
MILESTONE 2
M2 — Sign ICLAs in Self Serve · Effort: M (×3 platforms)
• PR check link lands in SS; individual flow completes DocuSign ceremony; back to PR, check green
• The “DocuSign problem” is smaller than feared: consoles never talk to DocuSign — SS won't either
  – One API call returns sign_url; webhooks, PDFs, envelopes stay in EasyCLA v2/sign — no new bridge service
• Cutover = flip the SSM redirect parameter per environment; rollback identical
• Sub-milestones by platform: M2a GitHub → M2b GitLab → M2c Gerrit (verify each cutover switch exists first)
• Parity details: embargo/OFAC checkbox (client-side today!), earliest-PR-only update + /easycla re-check
• Trickiest bit: preserving deep-link context through the Auth0 login round-trip

## Slide 8
MILESTONE 3
M3 — Corporate flow + ECLA in SS; retire Contributor Console · Effort: L
• Company search/add, pre-checks (sanctions, missing CCLA, approval list), ECLA acknowledgement (no DocuSign)
• Branches at parity: notify CLA managers · become CLA-manager designee · invite company admin
• Roles are assigned via existing v4 endpoints — no OpenFGA modeling needed yet; async ACS/Salesforce retries stay server-side
• Re-point notification emails that embed console URLs; redirect stub for old PR-comment links
• Console retires only after M3c (all three git platforms covered)
• Watch-out: designee flow hands off to Corporate Console until M4 — keep M3/M4 close on the roadmap

## Slide 9
MILESTONE 4
M4 — CCLA management in Organization lens; retire Corporate Console · Effort: XL
• Scope reality: not just ~160 Angular components — the console has its own GraphQL BFF (~648 files) to absorb
• Full inventory: CCLA signing (incl. email signatory — signs via DocuSign link, no LF account needed), 5 approval-list types, acknowledgements, manager CRUD, auto-create-ECLA, activity logs/CSV, metrics
• Role decision: bridge to EasyCLA/ACS (recommended) — OpenFGA copy now would be a second, non-enforcing source of truth
• CLA authority is finer-grained than org-lens b2b_org#writer — org admin ≠ CLA manager
• Dependency to confirm: Organization lens is currently dark-launched — GA timeline gates M4
• Freeze Corporate Console feature work at M4 start; golden-file parity checks (CSV, pagination, search)

## Slide 10
MILESTONE 5
M5 — EasyCLA project admin in Project lens; remove from PCC · Effort: L
• PCC v1 only (PCC v2 has no EasyCLA) — SS is the natural successor
• CLA group wizard (one CLA group per project; hierarchy validation), template preview/regeneration
• GitHub App install round-trip, per-repo enforcement, enforce-all; GitLab groups; Gerrit (list/link only — LF-hosted, ticket-based onboarding)
• Reporting incl. signature invalidation (destructive — confirmation + audit)
• Roles map naturally: project-scoped admin ≈ existing Project-lens authority (audit the 24-permission matrix first)
• Ops parity: repo lifecycle emails, default-branch-only auto protection, Merge Queue permission

## Slide 11
MILESTONE 6
M6 — Kubernetes V2 service; DynamoDB → Postgres? · Decision milestone
 | Track A: K8s, keep DynamoDB (XL) | Track B: A + Postgres (XXL)
Scope | Containerize (standalone server exists); fold in legacy /v1+/v2 surface; Heimdall + OpenFGA role migration (the hard part); aux lambdas; gradual gateway cutover | + repository-layer rewrite in every module; ~19-table migration with dual-run; replace DynamoDB-Streams event fan-out (outbox → NATS)
Risk | Authorization cutover (ACS→FGA) breaking corporate flows — dual-evaluate first | Signature data is legally meaningful — zero-loss required; migrate signatures table last
Recommendation: commit Track A only after M1–M5 prove the surface; run Postgres as a phased per-table strangler inside M6 (events first, signatures last). Interrogate the “DynamoDB causes issues” claim first — some pain is fixable with GSIs at 5% of the cost. Both API codebases are already Go — no language port anywhere.

## Slide 12
RISKS
Cross-cutting risks
Risk | Mitigation
Identity history: pre-LF-login records unlinked from LF accounts | M1 three-key union + GitHub-link CTA + unmatched telemetry (launch gate for M2)
Role bridging (ACS ↔ SS lenses) | Bridge, don't migrate, until M6; enforcement stays server-side in EasyCLA v4
Dual-console periods → feature drift | Freeze console feature work per area once its milestone starts; one release train for platform sub-milestones
Legacy /v1+/v2 Go surface drifts from /v4 | Single ownership; extend existing parity/contract tests; absorb in M6
Webhook/DocuSign callback loss at M6 cutover | Gradual gateway cutover + replay/reconciliation jobs
M6 discards M3–M5 adapters (rework) | Adapters deliberately thin (one SS server module); hybrid-strangler option if M6 committed early

## Slide 13
DECISIONS
Decisions resolved during spec review
• Q1 — Contributor login: already mandatory in the console today (verified in code) — SS introduces no new friction; no anonymous path needed
• Q2 — Git platforms: all three in scope; per-platform sub-milestones (M2a–c / M3a–c), each with its own cutover switch; console retires after M3c
• Q3 — Sequencing: UI-first (M1–M5 on existing v4 APIs, thin adapters); M6 separately gated
  – Alternative on the table: hybrid strangler — early CLA read/query V2 service after M2 if M6 becomes committed scope
• Everything above verified against code, not just docs (two doc claims corrected in the process)

## Slide 14
ASKS
What we need from this review
• Architecture: endorse the strangler strategy — SS as client of EasyCLA v4, roles bridged to ACS until M6
• Architecture: position on M6 (Track A / Track B / hybrid strangler timing)
• PM: approve milestone scope + parity contracts (inventory checklists per console)
• PM: confirm Organization-lens GA timeline (gates M4)
• EasyCLA team: review the one new endpoint (GET /v4/users/by-identity) and upstream hardening notes (ownership checks, embargo gate server-side, lf_username backfill)
• Next step: /speckit-tasks on M1 (plan approved and committed; specs on branch 001-easycla-ss-integration)